## Read me
Technical Debt Register
A register of technical debt: what it is, what it costs you, how much of a risk it carries and how hard it is to fix, with a priority rank and a decision for each item.
| Version | 1.0, 20 October 2026
| Published by | XONIK
How to use it
| Step 1 | Add one row for each item of technical debt. Name the system, describe the debt and say what kind it is.
| Step 2 | Score the impact on delivery, the risk of leaving it and the effort to fix it, each from 1 to 5. Impact and risk are high when they are bad. Effort is high when the fix is large.
| Step 3 | The priority score is impact times risk, divided by effort. The rank puts the highest score first. Choose a decision for each item, and name an owner and a review date.
| Step 4 | The Summary sheet counts items by decision and lists the top items. Review the register on a schedule and move decided items to Closed.
Limits
Cells with a blue tint are yours to change. White cells are calculated and should be left alone. Rows marked Example show how the formulas work and can be overwritten or deleted. This workbook is a working aid written by XONIK and is not legal, financial or technical-audit advice; it reflects the figures you enter and nothing else.

## Register
Debt register
One row for each item. Rows marked Example can be overwritten.
ID | System or area | The debt: what it is and why it is there | Kind | Impact on delivery (1-5) | Risk if left (1-5) | Effort to fix (1-5) | Priority score | Rank | Decision | Owner | Status | Review date | Notes
TD-01 | Billing service | Rules for each customer type are copied across four modules and change in different ways. | Code | 4 | 4 | 3 | 5.3333 | 1 | Schedule | Platform lead | Open
TD-02 | Order database | No tested way to restore from backup into a clean environment. | Infrastructure | 2 | 5 | 2 | 5 | 2 | Fix now | Head of operations | In progress
TD-03 | Reporting | Reports read from a copy that is refreshed by hand. | Data | 3 | 3 | 4 | 2.25 | 3 | Monitor | Data lead | Open
TD-04
TD-05
TD-06
TD-07
TD-08
TD-09
TD-10
TD-11
TD-12
TD-13
TD-14
TD-15
TD-16
TD-17
TD-18
TD-19
TD-20
TD-21
TD-22
TD-23
TD-24
TD-25
TD-26
TD-27
TD-28
TD-29
TD-30
TD-31
TD-32
TD-33
TD-34
TD-35
TD-36
TD-37
TD-38
TD-39
TD-40

## Lists
Lists
The choices offered in the register. Edit them to suit.
| Kind | Decision | Status
| Code | Fix now | Open
| Architecture | Schedule | In progress
| Tests | Monitor | Closed
| Infrastructure | Accept
Data
Documentation
Dependencies and security

## Summary
Summary
Counts and the top items update as you fill in the register.
|  | Decision | Items not closed
|  | Fix now | 1
|  | Schedule | 1
|  | Monitor | 1
|  | Accept | 0
|  | Total not closed | 3
| Rank | Item (system: debt) | Priority score
| 1 | Billing service: Rules for each customer type are copied across four modules and change in different ways. | 5.3333
| 2 | Order database: No tested way to restore from backup into a clean environment. | 5
| 3 | Reporting: Reports read from a copy that is refreshed by hand. | 2.25
4
5